## NCR report
[8 empty] | שם הקבלן / Name of Contractor |  | SHIKUN&BINUI Solel Boneh - Infrastructure & CHINA RAILWAY TUNNEL GROUP |  | שם פרוייקט / Project | S.C. Western Segment's Construction (SCW)
[8 empty] | שם מזמין / Company Name |  | NTA - Metropolitan Mass System Transit ltd. |  | חוזה מס' / Contract No | 10102432
[8 empty] | בקרת איכות / QC Company |  | Yugan Eng. ltd |  | הבטחת איכות / QA Company | Dana Eng. ltd
CAR / PAR Number | תאריך הפתיחה / Date of Opening | נפתח ע"י / NCR opened | דרגה / Detail | סוג / Type | גורם אחראי לליקוי (תכנון, ביצוע, ספק) / Responsible Party (Design ,Contractor,Supplier) | קטע (תחנה,כביש, מנהרה, גשר) / Element (Station, Road ,Tunnel , Bridge) | נושא / Topic | המלצה לשיפור/ CAR Reccomendation | גורם שורשי /Root Cause | פעולה מתקנת מוצעת על ידי הקבלן / Corrective action (proposed by Contractor) | Approximate closing date / תאריך סגירה משוער - אחרי מעודכן | פעולה מתקנת שבוצעה / Description of performed corrective action | תאריך סגירה / Date of closure | אישור מנהל ה"א לטיפול ב-PAR /CAR Approval of QA for performed corrective action | Open Beyond Expected Closure Date | הערות/ Remarks | Status (Open / Closed) / סטטוס (סגור/ פתוח)
QA/QC
מס'ד | תאריך כמו בNCR | כמו NCR | Major / Minor | PAR / CAR / OBS | TEXT | Allenby / Yehudit / Abba Hillel / Shaul HaMelech / Arlozorov / Abba Hillel / Bialik / Galei Gil / Herzl / TBM / Stations / General | TEXT | TEXT | TEXT | TEXT | like NCR | TEXT | like NCR | Approved / empty | YES / NO like NCR | TEXT | Open / Closed like NCR
1 | 2015-10-29 | QA | Minor | PAR | Contractor | Abba Hillel | Bored Piles | In review of the records of piles installed in the Abba Hillel UGS site, there is an evident confusion in the measures of lengths and volume. | The items to be measured are described in words which may be understood in more than one way. | Update the Bored Pile Record form to include a graphic sketch for filling in the measurements. Attached is an example. | 2015-11-05 | Updated the piles checklists to include a sketch with place to fill in measurements. |  |  |  |  | Closed / סגור
2 | 2016-07-05 | QA | OBS | OBS | Contractor | General | Preliminary Inspections | Approval of the Engineer for materials – submittals for approval are not complete and tracking of submittals and their response is not available to the QCEs on site. | The project includes 6 stations, each of which has its own QC Engineer(s) and not all engineers are aware of material approvals from other stations which may be applicable to their station. | Additional Training session for all QC Engineers on accessing Material approvals in YuganSoft. Recommend to review material approvals in the QA/QC weekly meeting. | 2016-09-05 |  |  |  |  | #01 - From QA Audit Report Doc. Ref: 740836 SCW-LP (XA-01#) | Open / פתוח
3 | 2016-07-05 | QA | Minor | CAR | Contractor | General | Meeting Minutes | Records of the Kick-Off meetings should be attached to each “Proof of Capability”/Mock-Up report. |  | Kick-off meeting minutes will be uploaded to YuganSoft. Kick-off meetings which relate to a POC will be attached to the POC | 2016-09-05 |  |  |  |  | #02 - From QA Audit Report Doc. Ref: 740836 SCW-LP (XA-01#) | Open / פתוח
4 | 2016-07-05 | QA | Major | CAR | Contractor | General | Document Manangement | Naming of QC records (checklists, lab tests etc.) should be corrected to comply with the QMS file naming procedure. | These documents are currently not mentioned in the file naming Procedure. | Update QMS Procedure CSJV-SB-JV-MSP-QMS-0029 Document Numbering and Coding Procedure | 2016-09-05 |  |  |  |  | #03 - From QA Audit Report Doc. Ref: 740836 SCW-LP (XA-01#) | Open / פתוח
5 | 2016-07-05 | QA | Major | CAR | Contractor | General | Lab Orders | Lab test results are commonly received only in a ‘temporary format’. These should include the laboratory logo and an authorized signatory signature. | The laborartory has not sent in the "Permanent lab report" on time. | Any temporary lab reports must be followed up by "Permanent Lab Report" which will be signed and bear the logo of the lab. | 2016-09-05 |  |  |  |  | #04 - From QA Audit Report Doc. Ref: 740836 SCW-LP (XA-01#) | Open / פתוח
6 | 2016-07-05 | QA | Minor | CAR | Contractor | General | Shop Drawings | Management of Construction Drawings and related Shop Drawings – the process requires improvement to ensure that all the works are done in accordance with up-to-date details. Approved Shop Drawings were missing in all sites -either the list (Master Index) was not up-to-date or drawings on site were not in accordance with the list. | Shop drawings are all in various stages of approval - this is an on-going process. | All approved shop drawings must be stamped "For Construction" by Dana Engineering, and then provided to the QC and On-site Engineers. | 2016-09-05 |  |  |  |  | #05 - From QA Audit Report Doc. Ref: 740836 SCW-LP (XA-01#) | Open / פתוח
7 | 2016-07-05 | QA | OBS | OBS | Contractor | General | Tracking Progress of Work | Control of activities (work batches) can be improved – currently, in most of the sites the control is done on top of a wall hanged site plan drawing without showing the progress of follow-up activities (tests, as-made). | The real control of activities and work batches is done in YuganSoft through the Project Tree. | Currently, the following types of files can be attached to any line in the Project Tree: NCR, SSR, RFI, As-Mades, Inspection Checklists. | 2016-08-05 | Currently, the following types of files can be attached to any line in the Project Tree: NCR, SSR, RFI, As-Mades, Inspection Checklists. |  | Request to close this OBS. |  | #06 - From QA Audit Report Doc. Ref: 740836 SCW-LP (XA-01#) | Open / פתוח
8 | 2016-07-05 | QA | Minor | CAR | Contractor | General | CAR / PAR Summary | The system for logging and tracking CARs and PARs is not in place yet. It is recommended to initiate the system per the Quality Plan. |  | This CAR / PAR summary sheet will be tracked manually for now, and will be incorporated into YuganSoft at a later time | 2016-08-05 | This CAR / PAR summary sheet will be tracked manually for now, and will be incorporated into YuganSoft at a later time |  | Request to close this CAR |  | #07 - From QA Audit Report Doc. Ref: 740836 SCW-LP (XA-01#) | Open / פתוח
9 | 2016-07-05 | QA | Minor | CAR | Contractor | General | NCR Management | Handling of open NCRs can be improved. There is a significant delay in provision of proposed corrective actions by the Contractor. The list of these NCRs is now tracked twice a month, so improvement is noticed. Specific problems in construction of the D-Walls (verticality, steel congestion in the overlap between two parts) are taking too long to correct. | Certain NCRs take a long time to correct when they require direction from the Designer or Supplier. | QC will continue to bring these NCRs to the forefront of weekly meetings to help move things along. | 2016-09-05 |  |  |  |  | #08 - From QA Audit Report Doc. Ref: 740836 SCW-LP (XA-01#) | Open / פתוח
10 | 2016-07-05 | QA | OBS | OBS | Contractor | General | Checklists for Roadworks / Temporary Deck / Utilities | Quality Records of roadworks, temporary deck (Yehudit Station) and utility works are not filled in real-time and improvements are required. It is noted that ITPs for these works were prepared by the Contractor and approved for use by the Engineer in recent months and their implementation is still underway. This item shall be reviewed in more details in the next audits planned for each station separately. | The checklists are filled in real-time on paper but not in the YuganSoft program - root causing being that the computerized checklists were not installed in the program at the time. | The checklists for roadworks, steel assembly, and utilities have been added to YuganSoft. Installation of Precast will be added soon. All checklists will be uploaded to the program. | 2016-09-05 |  |  |  |  | #09 - From QA Audit Report Doc. Ref: 740836 SCW-LP (XA-01#) | Open / פתוח
11 | 2016-07-05 | QA | Major | CAR | Contractor | General | Filling out checklists in Real-time | Opening of a new work batch checklists should be done in real-time. Some delays in were noted in the Audit and were noted in the Audit Checklist for each station. Improvement in timing is expected by the next audit planned. | The checklists are filled in real-time on paper but not in the YuganSoft program - root causing being that the computerized checklists were not installed in the program at the time. | All checklists will be opened in real-time. | 2016-09-05 |  |  |  |  | #10 - From QA Audit Report Doc. Ref: 740836 SCW-LP (XA-01#) | Open / פתוח
12 | 2016-07-06 | QA | Major | CAR | Contractor | General | RFI / DSI / SSR Tracking | RFIs/DSIs/SSRs – tracking is done separate to the records of the work batches. The current system by the Contractor does not allow for appropriate tracking of relevant changes/new details and comments on the construction by the Designer. A significant improvement of the process for tracking the designers information is required and will be reviewed in the next audit. | RFI's and Designer's reports were not attached to the checklists - however this was alrady corrected. | Currently, the following types of files can be attached to any line in the Project Tree: NCR, SSR, RFI, As-Mades, Inspection Checklists. | 2016-08-05 | Currently, the following types of files can be attached to any line in the Project Tree: NCR, SSR, RFI, As-Mades, Inspection Checklists. |  | Request to close this CAR |  | #11 - From QA Audit Report Doc. Ref: 740836 SCW-LP (XA-01#) | Open / פתוח